## Dashboard
Swapnil Wale | Project BRMS Tech |  |  |  | 2022-10-01
Open Risks (Rating) |  | Open Issues (Severity) | Open Action Items | Open Change Requests |  | Pending Decisions
|  |  | 4 | 2 |  | 1
Schedule Health
Task Status
Budget Health
Resource Health

## Schedule
BRMS Implementation |  | View Start |  |  | 2016-05-05 | Timeline |  |  | days | 1 | 2016-05-05 | 2016-05-06 | 2016-05-07 | 2016-05-08 | 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-13 | 2016-05-14 | 2016-05-15 | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-21 | 2016-05-22 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | 2016-05-28 | 2016-05-29 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25 | 2016-06-26 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01 | 2016-07-02 | 2016-07-03 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-09 | 2016-07-10 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15 | 2016-07-16 | 2016-07-17 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22 | 2016-07-23 | 2016-07-24 | 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28 | 2016-08-29 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-09-02 | 2016-09-03 | 2016-09-04 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-10 | 2016-09-11 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-15 | 2016-10-16 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-22 | 2016-10-23 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-10 | 2016-12-11 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-17 | 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24 | 2016-12-25 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2016-12-31 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18
# | Task Name | Resource | Pre | Start | Finish | Effort (days) | % | % | % | Status
[5 empty] | Auto |  | Act | Plan | Plan |  | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
1 | Requirement Gathering | John |  | 2016-05-05 | 2016-06-08 | 25 | 94% | 6688% | 100% | 6% | bar: T to M; T to M; T to M; T to M; T to M
2 | Draft Business Requirements | John | 1 | 2016-05-12 | 2016-05-16 | 3 | 94% | 55567% | 100% | 6% | bar: T to M
3 | Sign Off Business Requirements | John | 2 | 2016-05-17 | 2016-05-17 | 1 | 100% | 166400% | 100% | 0%
4 | Draft Functional Requirements | John | 3 | 2016-05-18 | 2016-05-19 | 2 | 100% | 83150% | 100% | 0% | bar: T
5 | Sign Off Functional Requirements | John | 4 | 2016-05-20 | 2016-05-24 | 3 | 90% | 55367% | 100% | 10% | bar: F to M
6 | Requirements Discussions | John | 5 | 2016-05-25 | 2016-05-26 | 2 | 100% | 82900% | 100% | 0% | bar: T
7 | High Level Design | Developer | 6 | 2016-05-27 | 2016-05-30 | 2 | 98% | 82800% | 100% | 2% | bar: F to M
8 | Detailed Design | Mich | 7 | 2016-05-31 | 2016-06-02 | 3 | 65% | 55133% | 100% | 35% | bar: T
9 | Detailed Design Review | Mich | 8 | 2016-06-03 | 2016-06-06 | 2 | 56% | 82550% | 100% | 44% | bar: F to M
10 | Design Sign Off | Mich | 9 | 2016-06-07 | 2016-06-07 | 1 | 78% | 164900% | 100% | 22%
11 | Design Review | Mich | 10 | 2016-06-08 | 2016-06-09 | 2 | 23% | 82400% | 100% | 77% | bar: T
12 | Design handover | Mich | 10 | 2016-06-08 | 2016-06-09 | 2 | 45% | 82400% | 100% | 55% | bar: T
13 | Analysis | Bob | 11 | 2016-06-10 | 2016-06-13 | 2 | 0% | 82300% | 100% | 100% | bar: F to M
14 | Build Component 1 | Bob | 12 | 2016-06-10 | 2016-06-15 | 4 | 0% | 41150% | 100% | 100% | bar: F to M
15 | Build Component 1 | Bob | 13 | 2016-06-14 | 2016-06-14 | 1 | 0% | 164400% | 100% | 100%
16 | Build Component 2 | Bob | 14 | 2016-06-16 | 2016-06-20 | 3 | 0% | 54733% | 100% | 100% | bar: T to M
17 | Build Component 3 | Bob | 15 | 2016-06-15 | 2016-06-21 | 5 | 0% | 32860% | 100% | 100% | bar: T to M
18 | Build Component 4 | Bob | 16 | 2016-06-21 | 2016-06-22 | 2 | 0% | 81950% | 100% | 100%
19 | Build Component 5 | Bob | 17 | 2016-06-22 | 2016-06-24 | 3 | 0% | 54600% | 100% | 100% | bar: T to F
20 | Build Component 6 | Bob | 11 | 2016-06-10 | 2016-06-13 | 2 | 0% | 82300% | 100% | 100% | bar: F to M
21 | Build Component 7 | Bob | 19 | 2016-06-25 | 2016-06-29 | 4 | 0% | 40875% | 100% | 100% | bar: S to M
22 | Build Component 8 | Bob | 20 | 2016-06-14 | 2016-06-15 | 2 | 0% | 82200% | 100% | 100%
23 | Build Component 9 | Bob | 21 | 2016-06-30 | 2016-07-01 | 2 | 0% | 81600% | 100% | 100% | bar: T to F
24 | Build Component 10 | Bob | 22 | 2016-06-16 | 2016-06-17 | 2 | 100% | 82100% | 100% | 0% | bar: T to F
25 | Integration Testing | Bob | 23 | 2016-07-02 | 2016-07-06 | 4 | 45% | 40750% | 100% | 55% | bar: S to M
26 | Analysis & test plan | Raven | 24 | 2016-06-18 | 2016-06-20 | 2 | 0% | 82000% | 100% | 100% | bar: S to M
27 | Create test cases | Developer | 25 | 2016-07-07 | 2016-07-08 | 2 | 0% | 81350% | 100% | 100% | bar: T to F
28 | Review test cases | Raven | 26 | 2016-06-21 | 2016-06-22 | 2 | 0% | 81950% | 100% | 100%
29 | Create test steps | Raven | 27 | 2016-07-09 | 2016-07-13 | 4 | 0% | 40625% | 100% | 100% | bar: S to M
30 | Review test cases | Raven | 28 | 2016-06-23 | 2016-06-24 | 2 | 0% | 81850% | 100% | 100% | bar: T to F
31 | Test Plan sign off | Raven | 29 | 2016-07-14 | 2016-07-15 | 2 | 0% | 81100% | 100% | 100% | bar: T to F
32 | Test Component 1 | Jhoti | 24 | 2016-06-18 | 2016-06-18 | 1 | 0% | 164000% | 100% | 100% | bar: S
33 | Test Component 2 | Jhoti | 31 | 2016-07-16 | 2016-07-16 | 1 | 0% | 162000% | 100% | 100% | bar: S
34 | Test Component 3 | Jhoti | 32 | 2016-06-19 | 2016-06-20 | 2 | 0% | 82000% | 100% | 100% | bar: S to M
35 | Test Component 4 | Jhoti | 33 | 2016-07-17 | 2016-07-17 | 1 | 0% | 162000% | 100% | 100% | bar: S
36 | Test Component 5 | Jhoti | 34 | 2016-06-21 | 2016-06-21 | 1 | 0% | 163900% | 100% | 100%
37 | Test Component 6 | Jhoti | 35 | 2016-07-18 | 2016-07-18 | 1 | 0% | 162000% | 100% | 100% | bar: M
38 | Test Component 7 | Jhoti | 36 | 2016-06-22 | 2016-06-24 | 3 | 0% | 54600% | 100% | 100% | bar: T to F
39 | Test Component 8 | Jhoti | 37 | 2016-07-19 | 2016-07-19 | 1 | 0% | 161900% | 100% | 100%
40 | Test Component 9 | Jhoti | 38 | 2016-06-25 | 2016-06-25 | 1 | 0% | 163500% | 100% | 100% | bar: S
41 | Test Component 10 | Jhoti | 39 | 2016-07-20 | 2016-07-22 | 3 | 0% | 53933% | 100% | 100% | bar: T to F
42 | Test Component 11 | Jhoti | 40 | 2016-06-26 | 2016-06-26 | 1 | 0% | 163500% | 100% | 100% | bar: S
43 | Performace Testing 1 | Jhoti | 41 | 2016-07-23 | 2016-07-26 | 3 | 0% | 53833% | 100% | 100% | bar: S to M
44 | Performance Testing 2 | Jhoti | 42 | 2016-06-27 | 2016-06-29 | 3 | 0% | 54500% | 100% | 100% | bar: M
45 | Components 1,2 | Bob | 43 | 2016-07-27 | 2016-07-29 | 3 | 0% | 53767% | 100% | 100% | bar: T to F
46 | Components 3,4 | Bob | 44 | 2016-06-30 | 2016-07-01 | 2 | 0% | 81600% | 100% | 100% | bar: T to F
47 | Components 5,6 | Bob | 45 | 2016-07-30 | 2016-08-02 | 3 | 0% | 53667% | 100% | 100% | bar: S to M
48 | Components 7,8 | Bob | 46 | 2016-07-02 | 2016-07-04 | 2 | 0% | 81500% | 100% | 100% | bar: S to M
49 | Components 9,10 | Bob | 47 | 2016-08-03 | 2016-08-04 | 2 | 0% | 80400% | 100% | 100% | bar: T
50 | Draft a plan |  | 48 | 2016-07-05 | 2016-07-06 | 2 | 0% | 81450% | 100% | 100%
51 | Conduct a dry run |  | 49 | 2016-08-05 | 2016-08-09 | 3 | 0% | 53533% | 100% | 100% | bar: F to M
52 | Fix the issues |  | 50 | 2016-07-07 | 2016-07-08 | 2 | 0% | 81350% | 100% | 100% | bar: T to F
53 | Report |  | 51 | 2016-08-10 | 2016-08-12 | 3 | 0% | 53433% | 100% | 100% | bar: T to F

## Budget
Resource Costs |  |  | Equipment Costs |  |  | Other Costs
Item | Estimated | Actual | Item | Estimated | Actual | Item | Estimated | Actual
Resourcing Costs | 750000 | 297000 | Pump Supplies | 12000 | 0 | Wet Weather Delay | 5000 | 2000
Consulting Costs | 50000 | 35000 | Truck hire | 57000 | 0 | Stakeholder Meeting | 1000 | 0
Training Costs | 25000 | 1500 | Professional Service Fees | 25000 | 200 | Marketing Plan | 500 | 200
|  |  | IT Costs | 4000 | 1000 | Conference Room Hire | 1200 | 1000
|  |  | Labor Cost | 2000 | 1500
|  |  | Testing Tool Licensing Cost | 5000 | 0
|  |  | Developer Tool Cost | 4000 | 2000
Total Cost | 825000 | 333500 | Total Cost | 109000 | 4700 | Total Cost | 6500 | 2200
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shoule we separate human resources , equipment, IT, etc ?

## Resources
Resource | Type | Rate | Days | Tasks | Cost | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20
John | Analyst | 500 | 90 | 36 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Mich | SME | 500 | 90 | 10 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Bob | Tester | 300 | 90 | 48 | 27000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Matt | SME | 500 | 90 | 0 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Raven | SME | 500 | 90 | 12 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Jhoti | Tester | 500 | 90 | 22 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Sam | Developer | 500 | 90 | 0 | 45000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5

## Risks
# | Risk Title | Risk Description / Impact | Status | Owner | Identified Date | Risk Category | Risk Rating | Possible Mitigation | Date Closed
001 | Tool License Expiry | Tool license expires in 3 months. This can halt development work. Cost not factored in the budget. | New | SRK | 2020-02-12 | Project | High
002 | Equipment Supplies | The supplier has indicated that all supplies cannot be delivered by project dates due to delivery delays post COVID. Development phase could be delayed. | WIP | MSD | 2020-03-12 | Organizational | High
003 | Design Issues | The application design was not reviewed by the traffic manager | On Hold | RNW | 2020-02-13 | Resource | Medium
004 | Stakeholder Involvement | Our customers are not ready for the change. | WIP | SRW | 2020-05-14 | Environment | Low

## Issues
# | Issue Title | Issue Description | Reported On | Reported By | Owner | Severity | Priority | Status | Comments
1 | Code Module Issue | An issue with code module was recently identified. The user is not able to make changes to the rates. | 25/2/2020 | Neel | Julie | Low | High | New | SRW 07-Feb : New Issue logged today.
2 | User Access Issue | Some of the users are not able to login. | 2020-03-03 | Swapnil | Kamel | Medium | Urgent | WIP | SRW 25-Mar : Issue is affecting service levels.
3 | Server Memory Issue | One of the server mmx0013 has memory issues and needs to be looked at. This memory issue is causing a performance issue with the application. | 26/3/2020 | Jack | Cathy | High | High | WIP
4 | User Interface Issue | Users are not able to make changes to certain fields when updating. | 2020-01-04 | Sam | Julie | Critical | Medium | OnHold | SRW 05-Apr : On Hold due to business confirmation.
5 | Spelling Error | One of the fields has a spelling error. | 2020-01-05 | Neel | Jim | Critical | Low | WIP | SRW 04-Apr : New Issue.

## Actions
# | Action Item | Owner | Due Date | Status | Priority | Comments
1 | Take Backup of the files | SRW | 2016-02-14 | Closed | Urgent | This is critical for the project.
2 | Check with SME for QA results | SRK | 2016-03-13 | Closed | High
3 | Talk to Sponsor for extra funding | MSD | 2016-06-11 | Open | Medium
4 | Process the invoices with Finance | PCK | 2016-05-19 | Open | Low
5 | Process the invoices with Finance | PCK | 2016-05-19 | Open | Low
6 | Process the invoices with Finance | PCK | 2016-05-19 | Open | Low

## Change Requests
# | Change Description | Requester | Priority | Date Raised | Decision | Decision Date | Comments
0001 | Component not estimated. | XYZ | Urgent | 2020-12-12 | On Hold | 2015-01-12 | Schedule impact of 2 months and budget impact of $150,000.
0002 | UI Design Contract | ZDB | High | 2020-04-12 | Approved | N/A | Budget Impact of $20,000.
0003 | New Workflow Option | DFG | Medium | 2020-01-12 | Approved | N/A | Schedule impact of 1 week.
0004 | New Field Needed | SRW | Low | 2020-01-13 | Rejected | N/A | Dev effort of 1 day.

## Decisions
# | Decision Details | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Resulting Action/Comments
1 | Increase the scope of the project to include UI testing. The initial scope of the project did not include UI Testing. | The project go live will be delayed by 3 weeks. | 2015-07-26 | Team | Closed | Manager | 2015-09-30 | The project plan will be changed to include additional effort of 3 weeks. Action item assigned to project manager.
2 | Additional requirements added to the project scope. Change Request #002. | No material impact on the project delivery date. | 2015-03-23 | SME | Closed | Project Control | 2015-09-30 | Approved as no material impact.
3 | Logo design cost of $5,000 not included in the initial budget. The logo design is needed as a standard. | The project cost will go up by $5,000. | 2015-06-25 | Marketing | Closed |  |  | Waiting Approval
4 | The HR Module from the application will be descoped as the business requirements are not finalized. | The HR team will have to use the legacy system. A separate project will need to be initiated to build the HR System. | 2015-06-24 | Project Manager | Closed |  |  | Abandoned as not needed.
5 | Add additional resources to bring in the project go live date. 3 developers and one tester will be needed to get the go live date to 3rd Sep. | Resources will need to be contracted which will cost the project additional $45,000. | 2015-08-25 | Team | New |  | 2015-08-27 | The decision recommendation was declined as no additional funding is available.

## Config
Sl. No | Public Holidays | Date | Severity | Priority | Status | Risk Category | Risk Rating | Approval | Resource Type
1 | Test |  | Critical | Urgent | New | Project | Critical | Approved | Developer
2 | Test |  | High | High | WIP | Organizational | High | Rejected | DBA
3 | Test |  | Medium | Medium | Closed | Resource | Medium | On Hold | Tester
4 | Test |  | Low | Low | On Hold | Environment | Low | New | Analyst
5 |  |  |  |  | Open |  |  | WIP | SME
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Data
DO NOT EDIT ANYTHING IN THIS SHEET
Task Count |  | Task % Complete |  | Budget |  |  |  |  | Resource |  | %
Total | 53 | Not Started | 39 | Costs |  | Planned | Spend | Remaining | Utilized | 128 | 20
Delay | 48 | Half Done | 3 | Resource Costs |  | 825000 | 333500 | 491500 | Availability | 630 | 80
On Track | 4 | Almost There | 9 | Software and HW |  | 109000 | 4700 | 104300 | Total | 758 | 100
Worry | 1 | Done | 4 | Other Costs |  | 6500 | 2200 | 4300
|  |  |  | Totals |  | 940500 | 340400 | 600100
Open Risks |  | Open Issues |  | Open Actions |  |  | Change Requests |  | Open Decisions
Critical | 0 | Critical | 2 | Urgent | 0 |  |  |  | New | 1
High | 2 | High | 1 | High | 0 |  | Rejected | 1 | WIP | 0
Medium | 1 | Medium | 1 | Medium | 1 |  | On Hold | 1
Low | 1 | Low | 1 | Low | 3 |  | New | 0 | On Hold | 0
|  |  |  | Total | 4 |  | WIP | 0 | Open | 0
[7 empty] | Total | 2 | Total | 1