## Risk
Implementation of Using Drone Technology for Bridge Inspection
Risk Table
Risk # | Risk | Probability | Impact | Risk Score |  |  | Probability
1 | The integration process is new and hasn't been field tested | 20% | 3 | 0.6 |  |  | 20% | 40% | 60% | 80% | 100%
2 | Not being able to recruit a developer for the drone tests | 60% | 4 | 2.4 | Impact | 5 | #5 ; #8 ; 10 |  | #7
3 | Legislation for drone use will not support roll out | 20% | 4 | 0.8 |  | 4 | #3 | #4 ; #9 | #2
4 | The shipment of the new field cameras will be late | 40% | 4 | 1.6 |  | 3 | #1
5 | The 3rd party contractor won't have sufficient personnel for fulfilling the contract | 20% | 5 | 1 |  | 2 |  |  |  | #6
6 | The Council won't approve the budget for the second phase | 80% | 2 | 1.6 |  | 1
7 | Insufficient trained staff to operate the drones | 60% | 5 | 3
8 | Cost of training | 20% | 5 | 1
9 | Resistance when system is implemented | 30% | 4 | 1.2
10 | The Council won't approve the current scope of the project | 20% | 5 | 1