Project Management Toolkit-Status Report 3 – 22 November 2020

Green	completed

Red	delayed

Currently in Process

- Writing of the final parts of the Guide and linking in the relevant tools.  Scheduling and project close tools are almost finalised and several tools are out for comment.

- Formatting the tools and adding badging

- Securing local councils to commence piloting

- Setting dates for the completion of piloting.

Anticipated date for the finalisation of the tools 21 December 2020 with availability on IPWEA web page by mid-February.  The initiation and planning phase tools will be ready for pilot by 30 November and it is hoped a local council will commence piloting these in early December.

Progress to Date

Project is running approximately one month behind original schedule and has maintained this level of creep since initiation.  This has been due to a number of factors including:

- Challenge to get the design of the tools and accompanying Guide suitable for the client group

- Time taken in sending tool out for review by project managers

- Limited availability of project engineering staff to develop and review the tools

- Leave taken by project manager

The final end date for the project has not changed.

Completed to Date

Consultation Report

Suites of tools for initiation, planning, risk management and cost estimating.

Issues/Risks

Insufficient time to pilot the tools as the end of the year approaches.  Project will lose three weeks from 18 December to 11 January due to public holidays, reduction in work flows within councils and staff leave.

As projects take time to deliver the pilot projects will need to be of a maximum of 6 months duration to meet final date.

Timeline