## Project Status
Weekly Status Report
Project Name |  | Children's Playground Upgrade |  | Project Manager |  | Tom Peters |  | Date | 2020-03-10
Project Health Card | [7 empty] | Green
Schedule |  | Green | The project tasks are on track.
Budget |  | Green | The budget is on track but some items are a concern but monitored.
Resources |  | Amber | The project is well resourced. Some resources have delivery delays and some people have taken unplanned leave
Quality |  | Green | No issues at present
Scope |  | Amber | The project scope is on track. There are 2 change requests pending.
Risks |  | Amber | Project Risks are under control.
Issues |  | Red | There are 4 high issues open.
Change Mgt |  | Green | The change management plan for the project is being drafted.
Project Schedule
No | Task |  |  | Start | Finish | Progress | Worst Date |  | Concerns
1 | Detailed Scope and Plan |  |  | 2020-01-14 | 2020-01-30 | 100 | 2020-01-30 |  | No
2 | Preliminary Earthworks and Drainage |  |  | 2020-01-30 | 2020-03-20 | 60 | 2015-03-31 |  | Yes
3 | Community Consultation |  |  | 2020-03-01 | 2020-04-30 | 50 | 2020-04-30 |  | No
4 | Playground Build |  |  | 2020-04-30 | 2020-05-15 | 10 | 2020-05-30 |  | No
5 | Quality Assurance |  |  | 2020-05-08 | 2020-05-20 | 0 | 2020-02-20 |  | No
6 | Project Close |  |  | 2020-05-20 | 2015-06-15 | 0 | 2020-06-15 |  | No
Project Financials
No | Item |  |  | Planned Spend |  | Actual Spend |  | Variance
1 | Wage and Contractor |  |  | 450000 |  | 250000 |  | 200000
2 | Playground Furniture |  |  | 75000 |  | 34000 |  | 41000
3 | Equipment Costs |  |  | 50000 |  | 23000 |  | 27000
4 | Earthworks Costs |  |  | 35000 |  | 40000 |  | -5000
5 | Other Expenses |  |  | 5000 |  | 3500 |  | 1500
Totals |  |  |  | 615000 |  | 350500 |  | 264500
Top 5
No | Type | Description |  |  |  | Status | Owner |  | Due
1 | Risk | There is a technical risk with the project which has not been addressed. |  |  |  | Red | Neal |  | 2015-01-12
2 | Issue | Some of the team members have taken unplanned leave. |  |  |  | Amber | Jim |  | 2021-03-20
3 | Decision | A key decision regarding playground furniture is pending. |  |  |  | Amber | Sam |  | 2015-02-23
4 | Dependency | The project has a depedency on other project for ground works which has not been resolved yet. |  |  |  | Red | Ram |  | 2015-04-26
5 | Change Request | The change requests need be approved at the earliest so that the impact on the project is less. |  |  |  | Green | Jam |  | 2021-03-20
Risks |  |  | Issues |  |  | Pending Items

## Data
Status | Items |  | High | Med | Low
Red | Risk | Risks | 5 | 2 | 2
Green | Issue | Issues | 4 | 2 | 3
Amber | Decision
| Action | Decisions | 2
| Dependancy | Actions | 3
| Assumption | Changes | 2
| Change Request | Dependancies | 5